## Sheet1
Date | Observe | Actions | Category | Person Responsible | Open/Closed | Comments
2002-08-29 | The bases and acids are stored next to each other on the same shelf in the same cabinet | They need to be moved |  |  | Closed | Following safe lab practice
2002-08-29 | Light on third floor exit sign is burnt out | Replace burnt out light |  |  | Closed | Reported to building attendant
2002-09-03 | Spiral stair case -- possible to bump head going up if tall | Install sign to watch head going up on spiral stair case |  |  | Open | Need to check head clearance vs. requests
2002-09-03 | Nitrogen Separator Equipment manual was bot found hanging near machine | Put manual near machine |  |  | Closed
2002-09-03 | Pumping A Impellers hanging on wall -- one fell right of onto floor | Use hooks instead of straight rods to hold impellers against wall and prevent from falling |  | Gasperich | Closed | Make new rack
2002-09-04 | CSTR unlabeled valves | Label valves on back of CSTR experiment |  |  | Closed
2002-09-05 | No sign on doors that steel toed shoes are required | Post signs warning of danger due to heavy things/chemicals to feet -- Steel toed shoes required. |  |  | Closed
2002-09-05 | Pumps not labeled on CSTR properly | Metal tags labeled P-1, P-2, P-3 would be appreciated |  |  | Closed
2002-09-10 | Sink in B003A is not enough to serve PDMS group and several labs. | Addition of an additional sink on the basement floor outside the B003A |  |  | Closed | Added distilled water tap in B003
2002-09-10 | Some of the syringes have extremely sharp tips | The stringes should have protective cover |  |  | Closed
2002-09-10 | No notebook at membrane separation station | Informed Dave -- Get notebook at station |  |  | Closed
2002-09-10 | Analytical balance was not tare | Calibrate balance |  |  | Closed | Students using balance in "calibration" mode
2002-09-10 | SE door exit light is out on first floor of lab | Replace bulb as sson as possible |  |  | Closed
2002-09-10 | Student came into lab without hard hat | Informed student |  |  | Closed
2002-09-10 | Group 7 not sign in or out |  |  |  | Closed
2002-09-10 | Remove chemical gloves before touching door handles | Reminded students to remove gloves |  |  | Closed
2002-09-10 | Groups should sign out when all members leave for lunch | Remind students to sign out |  |  | Closed | Remind in safety meeting
2002-09-10 | Dr. King had no steel toe shoes |  |  |  | Closed | Steel toes not required for those not doing lab work
2002-09-10 | No drain plugs in 2 drains by CSTR | Order drain plugs for drains |  |  | Closed | No potential for significant leak or spill
2002-09-10 | Pellets from the pelletizer go onto and all over the floor | We had to sweep it up often |  |  | Closed | Funnel is available
2002-09-10 | The transformer to turn on the extruder has it's switch on the left. Using the left hand rule puts your body in front of it | Move to the left and use the right hand so your body if not in front of it |  |  | Closed
2002-09-10 | Turn on the water using ladder, the valve is also hard to turn | Lower the valves so you can reach them from floor |  |  | Closed | Ladder is available in lab
2002-09-17 | Pumping A: Water leak after the feed tank at the first fitting | Should be repaired as soon as possible |  | Gasperich | Closed
2002-09-17 | Buffalo pump is leaking water | Should be repaired as soon as possible |  |  | Closed | Students had cooling water flow too high
2002-09-17 | Pumping A Impellers hanging on wall -- one fell right of onto floor | Use hooks instead of straight rods to hold impellers against wall and prevent from falling |  | Gasperich | Closed | Make new rack
2002-10-01 | PDMS lab manual is not up to date | Up to date manual should be in the lab |  |  | Closed
2002-10-01 | Heating mantle plug has 2 pronge plug |  |  |  | Closed | Heating wanted is fiberglass
2002-10-03 | Exit light on first floor -- south entrance is out | Fix as soon as possible |  |  | Closed
2002-10-08 | Outdated contact into for emergencies is listed | update phone number listing |  |  | Closed
2002-10-08 | Heat transfer experiment --emergency shut off valves are too high to reach if under 6' tall | Reported at oral presentation. Suggest adding a step |  |  | Closed | Ladder is available in lab
2002-10-08 | Black pipe directly over spectroscope in CSTR is leaking | Fix leak as soon as possible |  |  | Closed
2002-10-08 | Dow Corning 245 has 2 NFPA rating -- the labels were last updated 1995 | This was informed, PAWS form completed |  |  | Closed
2002-10-10 | Evacuation route sign on the south east door of the first floor lab is upside down | Change the sign to read correctly |  |  | Closed
2002-10-10 | Inspection tags hung on all eyewash & safety showers but not filled out | Fill out tags with info & date after inspecting them |  |  | Closed | Tags were recently replaced
2002-10-15 | Thursday's group left agitators pluged into socket on CSTR | Unplugged until experiment started |  |  | Closed
2002-10-15 | Safety shower SE corner first floor doesn't stay on when chain is pulled | Fix water valve as soon as possible |  |  | Closed
2002-10-15 | Fire Extinguishers need to be recharged | replace as soon as possible |  |  | Closed
2002-10-15 | Non-Newtonian flow - The capilary tube liquid blows on the pump where electrical coils are present | Build a shield |  |  | Closed | Added guard
2002-10-15 | Non-newtonian flow - pressure control valve located between V1 & V2 is not tagged | Suggest Tagging instrument |  |  | Closed
2002-11-05 | There is a leak from the floor above in the CSTR area (B005) | Keep the drip area clear and cleaned up the fluid |  |  | Open
2002-11-05 | Heat Exchanger -- One of the pneumatic controls is emitting a high squeal that may be unsafe | Verify safety |  |  | Closed
2002-11-05 | No log book at the new heat exchanger | Put one there |  |  | Closed
2002-11-05 | Membrane Separation -- "Analyzer Heater Power" label is confusing | Relabel all the switch |  |  | Closed
2002-11-07 | Student not wearing hard hat near cooling tower | Told him to put on |  |  | Closed
2002-11-12 | Liquid-liquid Extraction -- limited counter space | Add drying rack to the station |  |  | Open
2002-11-14 | Container labelled inconnectly in liquid-liquid extraction area | Called Tim |  | Gasperich | Closed
2002-12-03 | 100 ml volumetric flask for CSTR had no opening at the top | Replace a new one |  |  | Closed | Removed broken stopper
2002-12-05 | Student wearing running shoes, not steel toe | Notified student |  |  | Closed
2002-12-05 | No bucket used when carrying glassware up stair |  |  |  | Closed | Announcement to class at safety meeting
2002-12-05 | Poison information not properly attached to wall | lean over glassware box and retape |  |  | Closed
2003-02-06 | Dow 245 was spilled out of the can when rinsing T-201 | Don't tilt safety can so severly to cause liquid coming out of the can |  | Caspary | Closed
2003-02-25 | Valve head on DV-26 (SRU) is loose | Notified TA |  |  | Closed
2003-02-25 | 2 overhead lights on first floor are out |  |  |  | Open
2003-02-25 | PDMS reactor -- cooling water valve to overhead condenser was not opened according to procedure | Potential interlock should be explored to make sure valve is openned |  |  | Open
2003-02-25 | PDMS reactor catalyst was loaded before the inerting step | Distributed more copies of SOP throughout group |  |  | Open
2003-02-25 | TV210A leaking steam when controller output closed | Disassemble valve to find source of leak |  |  | Closed
2003-02-27 | Plug on vacuum pump in B003A has exposed wise | replace wire |  |  | Closed
2003-04-01 | SRU -- Check valve below DV-32 | Replace |  |  | Closed | Repiped the line back to feed tank
2003-04-01 | Group member was not wearing long sleeves when working with steam | Warned and the student put on a long sleeve lab coat |  |  | Closed | Added note in safety manual
2003-04-01 | When catching overhead sample for SRU, the bottle overflow & spill onto the floor | We cleaned up the mess with paper towel |  |  | Closed
2003-04-08 | SRU -- Spill Ethanol/Water overhead from column. Opened drain plug to get air out of process line for P-108 | Cleaned up spill |  |  | Closed | Repiped the line so there is no backpressure on pump
2003-04-08 | Did not complete safety checklist on run day 4/1/03 | Don't forget to do safety checklist |  |  | Closed
2003-04-08 | When testing shower, left it too long & make a gigantic spill | Make sure 2 people test safety shower |  |  | Closed
2003-04-15 | The safety shower and eyewash in Biolab have not been inspected in approximately a year | Inspected both shower and eyewash station. Both operate properly. |  |  | Closed
2003-04-15 | Person entered lab without hardhat on | mentioned |  |  | Closed
2003-04-17 | Student seen climbing ladder without it being held | Student notified ladder was held |  |  | Closed | Added note in safety manual
2003-04-17 | SRU -- hardhat removed while using hood for sample work | Offender was told to put hard hat on immediately |  |  | Closed
2003-04-17 | Person carried solution KOH in glassware up spiral staircase for PDMS | Person was told to take solution up stair, not spiral stair |  |  | Closed | Added note in safety manual
2003-04-22 | Appendix O for PDMS hard to follow closely. Could result in valve being placed in wrong position | Break up Appendix O, either through shuting or line breaks |  |  | Open