## Sheet1
Date | Observe | Actions | Category | Person Responsible | Open/Closed | Comments
2003-09-09 | Fire extinguishers not maintained B003 |  |  |  | Closed
2003-09-11 | Safety shower was creating a spill hazard around area | Shut off shower and used a squeqee to push water down the drain |  |  | Closed
2003-09-11 | No ear plugs available in lab office | Reported to Dave to refill ear plug container |  |  | Closed
2003-09-11 | Fire extinguishers out of date | Tols Tim and Dave |  |  | Closed
2003-09-23 | Glove chart for chemical handling | Post glove chart in the office for glove compatability for proper glove usage in each chemical |  |  | Open
2003-09-23 | Electrical cords are frayed at the liquid liquid separation lab | Replace hot plate or put a new cord on |  |  | Closed
2003-09-23 | Safety showers have no inspected tags | Make sure they worked and reported to safety coordinator |  |  | Closed
2003-09-23 | No earplugs in the office | Buy some earplugs |  |  | Closed
2003-09-23 | Student walked into the UO lab with no hard hat | Politely informed student to put on hard hat |  |  | Closed
2003-09-23 | Fire extinguisher on the first floor needs to be charged | Told Carrie |  |  | Closed
2003-09-23 | Fire extinguishers are not up to date | Have fire department come in to check extinguisher |  |  | Closed
2003-09-23 | Tables blocking fume hood entrance in room B003 | Moved tables so there was clear entrance to the fume hood |  |  | Closed
2003-09-23 | Electrical cord droped across floor can be tripped over | tried to move out at the way as we could |  |  | Closed
2003-09-25 | Window on first floor is broken | Signs are in place so they are not opened |  |  | Open
2003-09-25 | Multiple students removed hard hat and safety glasses while in lab | Individually reminded students to keep PPE on while inlab |  |  | Closed
2003-09-25 | Person was not wearing hard hat in designated area | Told subject that a hat was needed |  |  | Closed
2003-09-25 | Fire extinguishers had not been checked in over six months | Check pressure and signed off on tags if it was within range |  |  | Closed
2003-09-25 | Digital thermocouples stopped working at the Shell & Tube heat exchanger | Told Carrie |  |  | Closed
2003-09-25 | Digital thermocouples was carelessly immersed in water | Using non-digital gauges |  |  | Closed
2003-10-02 | Membrane Separator -- Analyzer cell is not up to date. It has exceeded replacement life | Brought it to TA |  |  | Closed
2003-10-28 | No tag on southeast door on first floor for shower/eyewash station. Rusty color water | Ran water for a while but no color change |  |  | Closed
2003-10-28 | Fire extinguisher blocked with trash can. Fire extinguishers are not up to date | Move item away from extinguisher. Testing the extinguisher |  |  | Closed
2003-10-28 | Non-newtonian flow -- the feed tank was leaking while foaming shift during the methanol run | Tightened it more and monitored if it would leak anymore |  |  | Closed
2003-10-28 | Non-newtonian Fluid -- dropped 50 ml beaker, broke on floor | Got dust pan to clean the floor |  |  | Closed
2003-10-30 | Update safety inspection form for PDMS bench | Safety can is needed for additional transfer of 245 solution outside the lab |  |  | Open
2003-10-30 | Under PPE checklist, dust masks and respirators in UO lab is no longer necessary | Remove line for checking off |  |  | Open
2003-10-30 | Student transported used shower curtain down spiral staircase | Transport shower curtain in elevator and wipe down slick steps |  |  | Closed
2003-10-30 | Fire extinguisher starting to become under pressure. | Pressurized and replace tag |  |  | Closed
2003-12-02 | Location of chemical storage and cabinet is unsafe. Sink and shower over flow water can run down the stair. Slip hazards | There is no sink or water near the middle drain. Move the chem storage cabinet to this position |  |  | Closed
2003-12-02 | Fire extinguisher in second level window side needs recharge | Recharge |  |  | Closed
2003-12-02 | Fire extinguisher tag needs to be replaced | Told supervisor to replace fire extinguisher |  |  | Closed
2003-12-02 | Hazard tags on non-newtonian water baths are illegible | Replace hazard tags on both water baths |  |  | Open
2003-12-02 | Eyewashes & safety showers in front of pumping and vacuum drying have rusty water | Flush out drains regularly |  |  | Closed
2003-12-02 | Safety showers in first floor storage and cabinet do not flow continuously when chain is pulled |  |  |  | Closed | This is how this type of safety shower works
2003-12-04 | The cooling tower drain pipe has a small leak in the first bend | Piping should be checked & tightened to make sure no leaks are present |  |  | Open
2003-12-04 | Fire extinguisher in 105 needs recharge | Barely into recharge area |  |  | Closed
2003-12-04 | Fire extinguisher in B005 needs recharge | Barely into recharge area |  |  | Closed
2003-12-04 |  | Hard hat was suggested in hard hat area |  |  | Closed
2004-02-12 | SRU ladders to reach the overhead valve | Need 2 people to handle ladder taller than 6 ft |  |  | Closed
2004-02-12 | The hydrometer used in SRU was dropped and broken on the floor | The broken glassware was cleaned and discarded |  |  | Closed
2004-02-26 | PDMS -- Toluene waste jar was sitting in the hood along with toluene and acetone bottles | Put back to the flammable cabinet |  |  | Closed
2004-03-23 | PDMS -- The valve tag for RV-40 is between valve and pressure regulator for CO2 tank | Move the valve tag to the left |  |  | Open
2004-03-23 |  | Each run day randomly choose a PAWS form from those submitted and give that person a prize
2004-03-30 | Second floor by SRU -- when pull off cap, it doesn't provide proper flow | Need to be replaced |  |  | Open
2004-03-30 | Fire extinguisher in control lab hasn't been checked since 02/03 | Notified lab supervisor |  |  | Closed
2004-03-30 | PDMS -- A ladder that didn't meet the height requirement was used while checking the valves | Informed individual of potential damage |  |  | Closed
2004-03-30 | SRU -- need someone to hold the ladder while they were on it |  |  |  | Closed
2004-03-30 | PDMS -- platform in northeast corner is loose | Needed tighten down |  |  | Closed
2004-03-30 | SRU -- Student didn't have assistant for ladder | Talked to the student and suggest to have a ladder assistant |  |  | Closed
2004-04-06 | First floor near SRU -- When removing eyewash cover, the ball on the right is stuck | Remove ball from cober and attach back in place |  |  | Open
2004-04-13 | The eyewash station in NW corner on second floor is broken | Need to be replaced |  |  | Open
2004-04-13 | Removal of hard hat and glasses | Brought to person attention |  |  | Closed
2004-04-13 | The SRU group wasn't holding the ladder | Suggest to have ladder asistant |  |  | Closed