## CM4110 & CM4120
Date | Observe | Description | Actions | Category | Person Responsible | Open/Closed | Comments
Open PAWS for past year as of 10/2/08
2006-01-31 | PDMS RV-5 on funnel: Install switch on RV-5 to allow for an interlock to be installed. This would help prevent pressurization of the line while funnel is being used. If possible, install additional system to prevent RV-5 from opening if line is pressurized |  | Class agreed a switch should be installed | Safety Suggestion | Dave | closed | vendor cannot find a switch for our application
2007-11-08 | Base spill supplies not clearly labeled on 1st floor. Could not find anything labeled for base cleanup on 1st floor |  | Recommend creating a base spill kit that is readily accessible and clearly labeled. | Safety Suggestion | Dave | closed | Base neutralizer is in cabinet under weighing bench.
2008-03-27 | Insulation on the 1st floor steam line next to the SRU is hanging and could fall on someone |  | Insulation fell off, not hazard anymore, needs replacement | Faulty Equipment | Tim | closed | Insulation replaced, 12/11/08
CM4110 2008
Cycle 1 & 2
2008-09-15 | Low hanging wire in B003B in walkway. Wire has poor insulation in this area. |  | Should get a longer, new cord and re-route it above the walkway. | Equipment Problem | Tim | closed | cords are supported from overhead racks
2008-09-16 | There is an extended cord from feeder 4 to the electrical outlet above the unit. If not in use disconnect cord to avoid someone bumping or getting caught going under the cord. Extruder experiment. More storage for the bags of polypropylene instead of stacking under table. Sweeping between groups near the outlet of the product to avoid build up on floors. |  |  | Safety Suggestion | Tim / Dr. King | closed | cords are supported from overhead racks
2008-10-02 | The emergency exit sign in room 213 (on the door) needs to be updated. |  |  | Signage | Dave | closed | sign was replaced, 11/4/08
2008-09-30 | Beaker was on the table, while cleaning out polarimeter tube, knocked beaker onto ground. |  | Swept up glass and placed into proper box. | Handling glassware |  | Closed
2008-10-02 | hand help thermometer was left on the floor, trip hazard. |  | Picked up thermometer and placed on work bench. | Housekeeping |  | Closed
2008-09-30 | For the fixed bed reactor experiment, one must remove their hard hats and safety glasses to use the polarimeter. |  | Extra precaution when using the polarimeter and putting PPE back on immediately after the reading. | PPE |  | closed | Class discussion determined that the polarimeter could be used with a hardhat on
2008-10-02 | I operated the steam valve on the shell and tube heat exchanger with my sleeves rolled up. |  | I was sure to roll my long sleeves down to full length for the remainder of the lab. | Other PPE |  | Closed
2008-10-02 | I lifted the 55 gal steel drum onto the scale unassisted. This is both unsafe and un-ergonomic as the drum weighs over 100 lbs. |  | Assistance was requested while moving the drum to ensure safety and prevent personal injury. | Misc. unsafe acts |  | Closed | Safe lifting video was shown in safety meeting on 10/24/08
2008-09-16 | Extruder lab, witnessed a female member of another lab group grab hot polymer as it left one of the MFI |  | Warned her | Chemical Handling |  | Closed
Cycle 3
2008-10-21 | Non-Newtonian Flow- The emergency shut off valve is placed too high, cannot reach it. |  | Kept step ladder near shut off | Safety Suggestion |  | closed | Valves are at eye level
2008-10-21 | Non-Newtonian Flow- The cooling water flow can splash out of the sink if the flow is set too high |  | put paper towels around sink to absorb splashes. | Misc. Equipment Problem |  | closed | added note to safety manual to keep cooling water flow to a minimum
2008-10-21 | Fuel Cell - Safety shower and eye wash has not been checked since 04/08. |  | Performed equipment inspection | Safety equipment |  | Closed
2008-10-21 | Room 105 cabinet drawer contained metal and glasswear near north door. |  | Removed metal instrument | Housekeeping |  | Closed
2008-10-21 | Water bottle brought to lab |  | removed from lab | Unsafe Act |  | Closed
2008-10-21 | Group members left 1 member attending to experiment |  | Alerted group of safety rules | Unsafe Act |  | Closed
2008-10-23 | Fixed Bed Reactor - On the lab stirrer motor, the drive shaft is not covered, this could be a hazard. |  | Covered spinning drive shaft | Safety Suggestion | Tim | closed | Motor is 1/75 hp and is easily stopped by hand.
2008-10-23 | Non-Newtonian Flow- Electrical outlet and cords are too close to the water tank. |  | Moved wires away from water, outlet is GFIC protected. | Housekeeping |  | Closed
2008-10-23 | Heat Exchanger - Barrel with lip needs to be replaced, causes too much splashing. |  |  | Misc. Equipment Problem |  | Closed | Other barrels are available in lab.
2008-10-23 | Fixed Bed Reactor - rubber hose causes back pressure when used to take a sample, decreases flow rate |  | Removed hose when sampling | Misc. Equipment Problem |  | closed
2008-10-23 | Heat Exchanger - not wearing proper PPE | Person was wearing only one thermal glove | Told them to put 2nd glove on | Improper PPE |  | Closed
2008-10-23 | Heat Exchanger - not wearing proper PPE |  | Did not handle condensate | Improper PPE |  | Closed
2008-10-23 | Individual not wearing long sleeves |  | Informed of infraction | Improper PPE |  | Closed
2008-10-23 | Water dripping from Pumping A experiment |  | Lowered cooling water rate | Leaks |  | Closed | added note to safety manual to keep cooling water flow to a minimum
2008-10-23 | Carrying too much down spiral staircase |  | Mentioned it was a hazard | Unsafe Act |  | Closed
2008-10-23 | Carrying open 5 gal jug of distilled water |  | Put cap on jug | Unsafe Act |  | Closed | reported twice, same incident
2008-10-23 | Carrying open 5 gal jug of distilled water |  | Put cap on jug | Unsafe Act |  | Closed | reported twice, same incident
2008-10-23 | Individual walking and texting with cell phone in lab |  | no action reported | Unsafe Act |  | closed
Cycle 4
2008-10-21 | The metal cover on the pump for non-Newtonian fluid is very hot. | The surface is right where samples are taken | Take special caution when taking samples. | Misc. Equipment Problem | Tim | closed | ventilation holes were added to the metal cover
2008-11-11 | There is a pipe that is not connecting to anything near the left side of cooling tower experiment in basement lab. | It can be a tripping hazard | The pipe should be removed | Safety suggestion | Tim | closed | the discharge end of the pipe is shortened
2008-11-11 | Pumping B leaks at PBV-05 and PBV-03 |  | reported problem | Leak | Dave | Closed | Tightened packing nuts.
2008-11-11 | PVC pipe draining water from cooling tower is a possible tripping hazard. |  | None | Safety suggestion | Tim | closed | It was painted yellow
2008-11-11 | Ladder blocks the measurement spot for the inlet air of the cooling tower |  | Measurements of the inlet air were taken once the ladder was no longer in use. | Safety suggestion |  | Closed
2008-11-11 | Site saver spray bottle in lab office is right at eye level. It can spray into someone's eye while using it. |  | None | Misc. Equipment Problem | Dave | Closed | Removed eywear cleaning station, disposed of the plastic housing and put the lense cleaner and lense wipes on the shelf in 105A.
2008-11-13 | Pumping A PA-V-13 is leaking |  | reported problem | Leak | Dave | Closed | Tightened packing nut.
2008-11-13 | Student did not have 3 points of contact when on ladder |  | None | ladder |  | closed
2008-11-13 | A container of mercury was found in cabinet B005B |  | None | Safety suggestion | Dave | closed | this has been disposed of
2008-11-13 | Released grip on ladder when a person is standing on the ladder. |  | None | ladder |  | closed
Cycle 5
2008-12-09 | A 55 gallon drum, used for the Heat Exchanger experiment, was leaking. |  | Drum was removed from the experimental area | Leak | Jerry | Closed | drum is no longer used
2008-12-13 | When cleaning CSTR, test tube fell and broke. |  | Notified TA, cleaned up broken glass, and disposed of in glass disposal container. | Handling Glassware |  | Closed | When using CSTR and hadling test tubes, be sure hands are dry and that test tube is set away from the edge of counter tops.
CM4120 2009
Cycle 1
2009-01-27 | PDMS scale reactor stirrer became stuck, upon increasing stirrer speed breifly to free it, solution escaped onto the heating element and caught fire |  | Fire was extinguished with a fire extiguisher, Dave and Tim were contacted | Spill |  | Closed | :Stirrer motor drive shaft is flexible, the shaft installation was modified to reduce a 180⁰ bend to a 90⁰ bend :The reactor will be loaded with 500mL of fluid instead of 750mL, and appropriate changes have been made to the JSA :The ground glass plug will be replaced with a plug that has a longer tapered section, other shorter plugs have been removed from the lab
2009-01-27 | A person entered the lab with out a hard hat. |  | The person was notified and instructed to put it on. | Hard Hat |  | Closed
2009-02-03 | Area around RV28 and RV29 is very hot, and could potentially cause a burn. |  | Put a warning note in the S.O.P. | Safety Suggestion | Dave | Open
2009-02-19 | A person on a ladder was not maintaining three points of contact. |  | Talked with the person to make them aware about the problem. | Ladder Safety |  | Closed
Cycle 2

## CM3215
Date | Observe | Description | Actions | Category | Person Responsible | Open/Closed | Comments
Fall 2008 CM3215
2008-09-23 | Leak under tanks between stations 3 and 4 |  | Water was mopped up and maintenance was notified | leaks | Jerry | Closed | leak repaired
Spring 2009 CM3215
2009-01-29 | Health NFPA Values contradicted each other on the Acetone MSDS |  | It will be assumed that acetone is a 2 for the Health Rating | MSDS | Dave | closed | MSDS shows NFPA and HMIS ratings for H-F-R. The NFPA rating is 1-3-0, the HMIS rating is 2-3-0. That's what they are. There is no contradiction.
2009-01-29 | Distilled water line needs to be labeled |  |  | Signage, tagging | Tim | closed | Pipe is labeled
`